## DAM3_TimeSheet
Quadcopter 2015 | [8 empty] | Version 1.0 | time axis 2015-07-06 to 2016-07-03
TaiVH - TuanTQ |  |  | Start Date | Planned End Date | Actual End Date | Work Days Planned | Work Days Elapsed | Work Days Remain | Work Days Overrun | 2015-07-06: 2015; 2015-07-13: 2015; 2015-07-20: 2015; 2015-07-27: 2015; 2015-08-03: 2015; 2015-08-10: 2015; 2015-08-17: 2015; 2015-08-24: 2015; 2015-08-31: 2015; 2015-09-07: 2015; 2015-09-14: 2015; 2015-09-21: 2015; 2015-09-28: 2015; 2015-10-05: 2015; 2015-10-12: 2015; 2015-10-19: 2015; 2015-10-26: 2015; 2015-11-02: 2015; 2015-11-09: 2015; 2015-11-16: 2015; 2015-11-23: 2015; 2015-11-30: 2015; 2015-12-07: 2015; 2015-12-14: 2015; 2015-12-21: 2015; 2015-12-28: 2015; 2016-01-04: 2016; 2016-01-11: 2016; 2016-01-18: 2016; 2016-01-25: 2016; 2016-02-01: 2016; 2016-02-08: 2016; 2016-02-15: 2016; 2016-02-22: 2016; 2016-02-29: 2016; 2016-03-07: 2016; 2016-03-14: 2016; 2016-03-21: 2016; 2016-03-28: 2016; 2016-04-04: 2016; 2016-04-11: 2016; 2016-04-18: 2016; 2016-04-25: 2016; 2016-05-02: 2016; 2016-05-09: 2016; 2016-05-16: 2016; 2016-05-23: 2016; 2016-05-30: 2016; 2016-06-06: 2016; 2016-06-13: 2016; 2016-06-20: 2016; 2016-06-27: 2016
Start | 2015-07-01
Today | 2015-08-27
ID | Task Description | WHO ?? | time axis 2015-07-06 to 2016-07-03
1 | Controller |  | 2015-07-20 | 2015-07-31 |  | 10 | 28 | 0 | 0
1.1 | Board nhận UART control 6 PWM | Tuấn | 2015-07-20 | 2015-07-24 |  | 5 | 28 | 0 | 0
1.2 | Bay thử | Tuấn | 2015-07-27 | 2015-07-31 |  | 5 | 23 | 0 | 0
1.3 | Mua controller + RCV | Tuấn | 2015-07-27 | 2015-07-31 |  | 5 | 23 | 0 | 0
2 | ĐỌC SOURCE KK2 |  | 2015-07-19 | 2015-08-08 |  | 15 | 28 | 0 | 0
2.1 | Code phần điều khiển, nhận tín hiệu điều khiển | Tuấn | 2015-07-26 | 2015-08-08 |  | 10 | 23 | 0 | 0
2.2 | Code điều khiển động cơ. Xem nó hoạt động như thế nào. | Tài | 2015-07-19 | 2015-07-25 |  | 5 | 28 | 0 | 0
2.3 | Code cho LCD | Tuấn | 2015-07-20 | 2015-07-25 |  | 5 | 28 | 0 | 0
2.3 | Code cảm biến nghiêng | Tài | 2015-07-19 | 2015-07-31 |  | 10 | 28 | 0 | 0
2.4 | Code PID, Matlab + simulink | Tài | 2015-08-04 | 2015-09-02 |  | 22 | 17 | 5 | 0
2.4 | Code cho bộ lọc | Tài | 2015-07-26 | 2015-08-01 |  | 5 | 23 | 0 | 0
3 | THIẾT KẾ VÀ CODE |  | 2015-08-01 | 2015-08-30 |  | 20 | 18 | 2 | 0
2.1 | Chọn VDK + IMU |  | 2015-08-02 | 2015-08-31 |  | 21 | 18 | 3 | 0
Debug bằng máy tính. Giao diện
2.2 | Code IMU mới |  | 2015-08-03 | 2015-09-01 |  | 22 | 18 | 4 | 0
2.3 | Code PWM mới |  | 2015-08-04 | 2015-09-02 |  | 22 | 17 | 5 | 0
2.3 | Code bộ nhận mới |  | 2015-08-04 | 2015-09-02 |  | 22 | 17 | 5 | 0
2.4 | Kết hợp code |  | 2015-08-04 | 2015-09-02 |  | 22 | 17 | 5 | 0
2.4 | Bay thử |  | 2015-08-05 | 2015-09-03 |  | 22 | 16 | 6 | 0
Tránh vật cản
Tìm hiểu các board xử lý ảnh. (raspherry pi, intel geogile)
Tìm đường bằng google map
Note on B6: Author: Bay xem chơi
Note on B10: Author: Hiểu và làm chủ source code
Note on B15: Author: Mô hình máy bay trên máy tinh. Hiểu các thông số điều khiển. Khả năng của Matlab
Note on B17: Author: Hiểu và làm chủ source code
Note on B25: Author: Sau bước này sẽ làm chủ phần mềm và phần cứng

## Settings (hidden)
Name | Value | Description
DateOffset | 1 | Used by the scrollbar. Do not manually change.
WeekStartType | 2 | Sets the day of the week to display as the start of the week (e.g. 2 = Monday).
GanttNoOfYears | 2 | Sets the date coverage of the Gantt chart (i.e. the latest date that can be displayed).
ShowFY | FALSE | Toggles between splitting years into Financial Years (e.g. 2009/10) or Calendar Years (e.g. 2009). Set to TRUE if you want to display Financial Years.